^T - A TASK MANAGEMENT SYSTEM

                                  REFERENCE MANUAL

                                    VERSION 1.11






















                                 Copyright (C) 1989
                                   Steve Starsinic
                              Hummelstown, Pennsylvania
                                 All Rights Reserved














                                                          TABLE OF CONTENTS


          Calculations.................................................. 4

               Calendar................................................. 4
               Project Costs............................................ 4
               Project Start And End Date............................... 4
               Resource Scheduled Task Efficiency....................... 4
               Task Adjusted Hours...................................... 5
               Task Costs............................................... 6
               Task Start And End Dates................................. 7

          Command Line.................................................. 7

          Conflicts..................................................... 8

               Age...................................................... 8
               Commitment Date.......................................... 8
               Priority................................................. 9

          Data Entry Screens............................................ 9

               Add/Subtract Hours....................................... 9
               Custom Calendar..........................................10
               Default Calendar.........................................10
               File Details.............................................11
               General Defaults.........................................12
               Load File Details........................................12
               Printer Driver Configuration.............................13
               Printer Options..........................................14
               Project Details..........................................15
               Project Details (Edit)...................................16
               Project Fields Displayed In Outline......................17
               Resource Details.........................................18
               Resource Fields Displayed In Outline.....................19
               Task Classifications.....................................19
               Task Details (Add).......................................20
               Task Details (Edit)......................................22
               Task Fields Displayed In Outline.........................24
               Video Configuration......................................25

          Files.........................................................26

               Archive (.RCV)...........................................26
               ASCII Data (.ASC)........................................27
               Configuration (.CFG).....................................28
               Print Buffer (PRINT.BUF).................................28
               Printer Driver (.DRV)....................................28
               Print File (.PRN)........................................29




                                        - 2 -




               Task Outline (.TSK)......................................29

          Keyboard......................................................30

               Main Screen Keys.........................................30
               Data Entry Keys..........................................31
               Quick Access Keys........................................32

          Main Screen...................................................33

          Menus.........................................................34

               Add......................................................34
               Configure................................................35
               Delete...................................................36
               Edit.....................................................36
               File.....................................................37
               Print....................................................38
               Rearrange................................................39

          Reports.......................................................39

               Fields Displayed In Reports..............................39

          Appendixes....................................................40

               A. Requirements/Limits...................................40
               B. Error Messages........................................41
               C. Video Handling........................................45
               D. Freeing Memory........................................46


























                                        - 3 -






                                                               CALCULATIONS
                                                                   CALENDAR


          ^T maintains a 5-year calendar.  The calendar starts on January 1
          of the year of the earliest resource start date, and ends on
          December 31 of the 4th following year.  Working days and Holidays
          are determined from the Custom Calendar.


                                                               CALCULATIONS
                                                              PROJECT COSTS


          Project costs are the sums of all the costs for the tasks
          currently linked to the project.


                                                               CALCULATIONS
                                                PROJECT START AND END DATES


          The project Start Date is the earliest Start Date of all the
          tasks linked to the project.

          The project End Date is the latest End Date of all the tasks
          linked to the project.


                                                               CALCULATIONS
                                         RESOURCE SCHEDULED TASK EFFICIENCY


          The Scheduled Task Efficiency for a resource is the factor used
          to expand the calculated working hours required to complete a
          task into a span of time on the calendar.  For example, if a task
          requires 10 working hours to complete, and the Scheduled Task
          Efficiency is 50%, the time used to plan the task on the calendar
          is 10 / .5 or 20 hours.

          Scheduled Task Efficiency is calculated as follows.

               ((Hours Per Work Week - Total Unscheduled Hours) /
                          Hours Per Work Week) * 100










                                        - 4 -






                                                               CALCULATIONS
                                                        TASK ADJUSTED HOURS


          Adjusted Hours are displayed in the 'Adj. Hrs. Remaining' field
          of each task record as a calculated, non-entry, field.  Adjusted
          hours are defined as the working hours remaining in the task
          adjusted for the resource's Scheduled Task Efficiency.  This
          number reflects the actual span of time on the calendar that will
          be required to complete the task.  Adjusted Hours are calculated
          as follows.

          1a. If no Act. Working Hours or O.T. Working Hours have been
          entered,

               Time Remaining = Est. Working Hours.

          1b. If Act. Working Hours or O.T. Working hours have been
          entered,

               a. Total Hours = Act Working Hours + O.T. Working Hours
               b. Time Remaining = Total Hours / (Percent Complete / 100)
               c. Time Remaining = Remaining Hours - Total Hours
               
          2a. If Adjust Working Days is set to 'YES'

               Adj. Hours Remaining = Time Remaining /
                                      (Scheduled Task Efficiency / 100)

          2b. If Adjust Working Days is set to 'NO'

               Adj. Hours Remaining = Time Remaining






















                                        - 5 -






                                                               CALCULATIONS
                                                                 TASK COSTS


          Three costs are calculated for each task: Predicted Cost,
          Incurred Cost, and Est. Final Cost.  Calculations for Predicted
          Cost and Incurred Cost are performed as follows:

               a. Rate = Hr. Rate (from resource)

               b. Predicted Cost = Rate X Est. Working Hours

               c. Incurred Cost = Rate X
                                  (Act. Working Hours + O.T. Working Hours)

          Est. Final Cost calculation is slightly more complicated, and is
          performed as follows

          1a. If no Act. Working Hours or O.T. Working Hours have been
          entered,

               Total Hours = Est. Working Hours.

          1b. If Act. Working Hours or O.T. Working hours have been
          entered,

               a. Total Hours = Act Working Hours + O.T. Working Hours
               b. Total Hours = Total Hours / (Percent Complete / 100)

          2.  Est. Final Cost is then based on Total Hours:

               Est. Final Cost = Total Hours X Rate






















                                        - 6 -






                                                               CALCULATIONS
                                                   TASK START AND END DATES


          The Start Date for the first task assigned to a resource is equal
          to the Start Date for the resource.  For all remaining tasks, the
          Start Date is equal to the Ending Date of the preceding task.

          The End Date is determined by adding the remaining days left in
          the task (Adj. Hours Remaining / Calendar Hours Per Work Day) to
          the Start Date.  Non-work days and Holidays (as specified in your
          Calendar) are skipped over.

          Notice that the remaining days left in the task can include
          fractional days (for example, 5.36 days).  ^T keeps track of
          fractional days internally, but does not display the fractional
          parts.  For example, if a task starts on 6/15 (+.00) and has .75
          days remaining, the End Date is 6/15 (+.75).  The next task will
          have a Start Date of 6/15 (+.75).

          Tasks that have End Dates exactly equal to the number of hours in
          a working day display the following date (.00) as the End Date.
          For example, if a task starts on 6/15 (+.75) and has .25 days
          remaining, the End Date is 6/16 (+.00).


                                                               COMMAND LINE


          Version 1.0 of ^T allows only one parameter on the command line:
          the name of the task file to automatically open.  Simply follow
          the program name (^T) with the name of the file, separated by a
          space.  For example, if you've created a task file called
          MYTASKS, to have ^T automatically open that file issue the
          following command:

                              ^T  MYTASKS

          ^T will load into memory and load the MYTASKS file.















                                        - 7 -






                                                                  CONFLICTS
                                                                        AGE


          The age of a task is the difference in calendar days (including
          weekends and holidays) between the current date and the date the
          task was entered in ^T.

          A task is considered Active if the task Status field is marked
          Active.  When Actual or O.T. hours are entered a task
          automatically becomes Active.  You can also manually change a
          task's status to Active.

          An Age conflict occurs when an Active task's Age exceeds the
          number of days entered into the Age Warning field in the General
          Defaults Screen.

          When an Age conflict occurs, an 'A' appears next to the task and
          the Conflict warning is turned on.

          Age conflicts can be removed by (1) changing the task to Active
          status or by raising the General Defaults Age Warning Level to a
          number exceeding the age.  Note however that the second solution
          is global and affects all tasks.

          The Age conflict is a warning only and does not affect
          calculations or dates.



























                                        - 8 -






                                                                  CONFLICTS
                                                            COMMITMENT DATE


          A commitment date conflict occurs when the Est. End Date of a
          task is later than either (1) the Commit Date for that task or
          (2) the Commit Date for a project to which it is linked.

          Commitment date conflicts are marked with a letter 'C' to the
          left of the task.

          To remove a commitment date conflict, (1) move the task higher in
          the outline so that calculated End Date precedes commit date, (2)
          change the commit date to a date later than the End Date, or (3)
          remove the Commit Date altogether.  Note that solutions (2) and
          (3) could also apply to a project Commit Date.

          If you elect to move the task to a higher position in the outline
          it is implied that this task becomes higher priority, or
          emphasized, in importance.  In other words, to complete this task
          on time, a certain amount of attention must be given it over the
          tasks following it in the outline.


                                                                  CONFLICTS
                                                                   PRIORITY


          A priority conflict occurs when a task with a higher priority
          (lower number) precedes a task with a lower priority (higher
          number).  For example, if a task with priority 50 precedes, or is
          higher than, a task with priority 40, the task with priority 50
          is marked as being in conflict.

          Priority conflicts are marked with a letter 'P' to the left of
          the task.  To remove a priority conflict, (1) move tasks so that
          the task with higher priority (lower number) precedes the task(s)
          with lower priority (higher number), or (2) change the priority
          numbers so that there is no conflict.















                                        - 9 -






                                                         DATA ENTRY SCREENS
                                                         ADD/SUBTRACT HOURS


          PURPOSE: To allow incremental additions to or subtractions from
          the Act. Working Hours or O.T. Working Hours fields on the Task
          Details (Edit) screen.

          ACCESS: With the cursor positioned in either the Act. Working
          Hours or O.T. Working Hours fields on the Task Details (Edit)
          screen. press either the '+' or '-' keys.

          FIELDS:

           1. Unnamed.  Enter a number from -999.99 to 9999.99.  This
          amount will be added to or subtracted from the original field.


                                                         DATA ENTRY SCREENS
                                                            CUSTOM CALENDAR
                                                           DEFAULT CALENDAR


          PURPOSE: Customize working calendar for a specific task outline.
          or the default calendar which is used to "seed" custom calendars
          when new task outlines are created.

          ACCESS: For the Custom Calendar, Select Edit on the main menu and
          Calendar on the Edit menu.  For the Default Calendar, select
          Configure on the main menu and Default Calendar on the Configure
          menu.

          FIELDS:

           1. Working Week.  7 fields, one for each day of the week.  Enter
          a 'Y' to mark the day as a working day, or 'N' to mark it as a
          non-working day.

           2. Hours Per Working Day.  Enter the number of hours that make
          up the work day, typically 8.00.

           3. Scheduled Holidays.  20 Sets of fields to describe specific
          non-working days.  For each Holiday, enter a description up to 20
          characters and a date.  The dates need not follow any particular
          order.









                                        - 10 -






                                                         DATA ENTRY SCREENS
                                                               FILE DETAILS


          PURPOSE: Provide a name and description for a task outline file.

          ACCESS: Select File from the main menu and Rename from the File
          menu, or select Edit from the main menu and File Description from
          the Edit menu.

          FIELDS:

           1. Description.  Enter a general description of the task
          outline.  This description will appear as a header for all
          reports.

           2. Path.  Enter the MS-DOS file path where the file is, or will
          be, located.  Do not include the filename in the path.

           3. File Name.  Enter an 8 character file name for the task
          outline.  The extension .TSK will be automatically appended.

































                                        - 11 -






                                                         DATA ENTRY SCREENS
                                                           GENERAL DEFAULTS


          PURPOSE: Set general system defaults.

          ACCESS: Select Configure from the main menu and General Defaults
          from the Configure menu.

          FIELDS:

           1. Manual Recalc.  YES/NO field.  YES indicates that
          recalculations are to be performed only at the command of the
          user.  NO indicates that recalculations are performed
          automatically when changes occur.

           2. Auto Update.  If auto update is set to Yes, then all resource
          start dates are automatically set to the current date when a task
          outline is loaded.  It is not recommended that this be done,
          since resource Start dates should generally only be changed when
          task data is updated.

           3. Age Warning Level.  Enter a number of days up to 999.  If an
          Inactive task's Age exceeds this number, an Age conflict occurs.

           4. Printer Driver.  A choice field.  Select the printer driver
          from the displayed table.  This driver becomes the installed
          driver for the system.



                                                         DATA ENTRY SCREENS
                                                          LOAD FILE DETAILS


          PURPOSE: Specify the path and file name for the task outline file
          to be loaded.

          ACCESS: Press F3, or select File from the main menu and Load from
          the File menu.

          FIELDS:

           1. Path.  Enter the MS-DOS path where the file is located.

           2. File Name.  Choice field.  Select the task file listed in the
          table.







                                        - 12 -






                                                         DATA ENTRY SCREENS
                                               PRINTER DRIVER CONFIGURATION


          PURPOSE: Configure either an existing or a new printer driver.

          ACCESS: Select Configure from the main menu and Setup Printer
          from the Configure menu.

          FIELDS:

           1. Name.  Enter file name for the driver.  The extension .DRV
          will automatically be appended when the file is saved.

           2. Port.  Choice field.  Select parallel or serial port where
          the printer is attached.

           3. Speed.  Choice field.  For serial printers, select the bps
          (bits per second) speed.  For parallel printers, this field is
          ignored.

           4. Char Format.  Choice field.  For serial printers, select the
          character format.  Table choices represent data-parity-stop
          values.  For parallel printers, this field is ignored.

           5. Out Device.  Choice field.  Select the device to which output
          is sent.  'Printer' results in normal printed output.  'Screen'
          will cause the output, formatted as though for a printer but
          minus special control codes, to be sent to the screen instead.
          'Print File' will cause the output, formatted as though for a
          printer but minus special control codes, to be sent to the disk
          file specified in the Out File field.  The Out File name will
          have the extension .PRN appended.  'ASCII Data' will result in
          the records being recorded in an ASCII Data file with fixed
          length records and no printer control codes or other formatting
          included.  The ASCII file will be the disk file specified in the
          Out File field with .ASC appended.  See FILES-ASCII for an
          explanation of the file format.

           6. Out File.  The filename to be used when the Out Device is set
          to either Print File or ASCII Data.

           7. Lines/Page.  Enter the number of physical lines that can be
          printed on your paper.  This would typically be 66 for dot matrix
          printers and 60 for laser and some ink jet printers, assuming
          that 6 lines per inch vertical spacing is used.

           8. Left Margin.  Enter the left margin size in number of
          characters.





                                        - 13 -




           9. Top Margin, and
          10. Bottom Margin.  Enter the margin in numbers of lines.

          11. Page Number.  Choice field.  Select the horizontal position
          of the page number.  Page number is always printed at the bottom
          of the page.

          12. Lines/inch.  Enter the vertical lines per inch as either 6 or
          8.  Entering depending on the setting of this field, either the
          control codes for the '6 lines/inch' or those for the '8
          lines/inch' fields will be sent to the printer.

          13. Title, and
          14. Headings, and
          15. Detail.  Choice fields.  Select the font or characteristic
          for each area from the table.  The control codes for the fonts
          selected will be sent to the printer.

          16. CONTROL CODES.  For all fields in this area, enter the
          printer control codes, in hex.  The last two lines are reserved
          for custom fonts.  You may enter both the name and the control
          codes.  If either or both of these are entered, they will appear
          in the choices table for fields 13, 14, and 15 above.



                                                         DATA ENTRY SCREENS
                                                            PRINTER OPTIONS


          PURPOSE: Make temporary changes to printer information
          immediately prior to printing a report.

          ACCESS: Displays automatically when any report is selected.

          FIELDS:

          See details of fields with same name under DATA ENTRY SCREENS,
          PRINTER DRIVER CONFIGURATION above.

















                                        - 14 -






                                                         DATA ENTRY SCREENS
                                                            PROJECT DETAILS


          PURPOSE: Add a new project to the task outline.

          ACCESS: Select Add from the main menu and Project from the Add
          menu.

          FIELDS:

          1. Description.  A text description of the project.

          2. Label.  A short (10 character) description of the project.
          The label is a required field and must be unique for each project
          (^T will enforce uniqueness).  The label fields make up an index
          to project records in that when adding or editing a task record,
          the project labels are used to make up a choice table.

          3. Number.  Optional.  Project id numbers or any other data
          desired by the user.  ^T makes no use of this field.

          4. Commit Date.  Optional.  A committed end date for the project.
          This commit date will be imposed on all tasks linked to the
          project.





























                                        - 15 -






                                                         DATA ENTRY SCREENS
                                                     PROJECT DETAILS (EDIT)


          PURPOSE: Edit an existing project record.

          ACCESS: Project records can be edited under two conditions.  (1)
          If the outline pointer is positioned on a task that is linked to
          a project, select Edit from the main menu and Project from the
          edit menu.  (2) If the outline is in Project outline mode (as a
          result of a Rearrange-Project command) and the outline pointer is
          positioned on a project, either press Enter, or select Edit from
          the main menu and Project from the edit menu.

          FIELDS:

           1. Description.  A text description of the project.

           2. Label.  A short (10 character) description of the project.
          The label is a required field and must be unique for each project
          (^T will enforce uniqueness).  The label fields make up an index
          to project records in that when adding or editing a task record,
          the project labels are used to make up a choice table.

           3. Number.  Optional.  Project id numbers or any other data
          desired by the user.  ^T makes no use of this field.

           4. Commit Date.  Optional.  A committed end date for the
          project.  This commit date will be imposed on all tasks linked to
          the project.

           5. Est Start Date.  Derived, non-entry.  The earliest start date
          for any task assigned to the project.

           6. Est End Date.  Derived, non-entry.  The latest end date for
          any task assigned to the project.

           7. Act Completion.  Derived, non-entry.  The latest completion
          date for any task assigned to the project.

           8. Predicted Cost.  Derived, non-entry.  The sum of the
          Predicted Costs for all tasks assigned to the project.

           9. Incurred Cost.  Derived, non-entry.  The sum of the Incurred
          Costs for all tasks assigned to the project.

          10. Est. Final Cost.  Derived, non-entry.  The sum of the Est.
          Final Costs for all tasks assigned to the project.






                                        - 16 -






                                                         DATA ENTRY SCREENS
                                        PROJECT FIELDS DISPLAYED IN OUTLINE


          PURPOSE: Configure the display of project records in the screen
          outline and in reports.

          ACCESS: Select Configure from the main menu and Project Fields
          from the configure menu.

          FIELDS:

          All fields are Yes/No fields.  There is a matching field for each
          field in a project record, including derived non-entry fields.
          If a YES appears in the fields, that field will be displayed in
          the outline.  If NO, the field is not displayed.






































                                        - 17 -






                                                         DATA ENTRY SCREENS
                                                           RESOURCE DETAILS


          PURPOSE: Add a new resource to the task outline.

          ACCESS: Select Add from the main menu and Resource from the add
          menu.

          FIELDS:

          1. Name.  A text description of the resource.

          2. Label.  A short (10 character) description of the resource.
          The label is a required field and must be unique for each
          resource (^T will enforce uniqueness).  The label fields make up
          an index to resource records in that when adding or editing a
          task record, the resource labels are used to make up a choice
          table.

          3. Number.  Optional.  Resource id numbers or any other data
          desired by the user.  ^T makes no use of this field.

          4. Start Date.  A starting date for the tasks assigned to the
          resource.  The first task in the outline assigned to this
          resource will have a start date equal to the date in this field.

          5. Hourly Rate.  The hourly rate for this resource at which task
          costs will be calculated.

          6. Unsch. Task Descs.  Enter a description for each of the
          unscheduled, unplanned, or unexpected  activities performed by
          this resource.  Typical entries would be for supervisory,
          administrative, phone, and non-work time.

          7. Unsch. Task Hours.  Enter the number of hours per week
          performed in each of these activities.

          8. Total Unsch. Hours.  Derived, non-entry.  The sum of all the
          weekly unscheduled hours.

          9. Sch. Task Eff.  Derived, non-entry  See CALCULATIONS, PROJECT
          SCHEDULED TASK EFFICIENCY for explanation of the calculation.
          This factor is used to adjust working hours to calendar duration
          hours.









                                        - 18 -






                                                         DATA ENTRY SCREENS
                                       RESOURCE FIELDS DISPLAYED IN OUTLINE


          PURPOSE: Configure the display of resource records in the screen
          outline and in reports.

          ACCESS: Select Configure from the main menu and Resource Fields
          from the configure menu.

          FIELDS:

          All fields are Yes/No fields.  There is a matching field for each
          field in a resource record, including derived non-entry fields.
          If a YES appears in the fields, that field will be displayed in
          the outline.  If NO, the field is not displayed.


                                                         DATA ENTRY SCREENS
                                                       TASK CLASSIFICATIONS


          PURPOSE: Configure the table of classifications that can be
          entered in a task record.

          ACCESS: Select Configure from the main menu and Classifications
          from the configure menu.

          FIELDS:

          All fields are text fields.  There can be up to 20 classes of the
          user's choice.  When editing a task record, a class from this
          table can be entered.





















                                        - 19 -






                                                         DATA ENTRY SCREENS
                                                         TASK DETAILS (ADD)


          PURPOSE: Add a new task to the task outline.

          ACCESS: Select Add from the main menu and Task from the Add menu,
          or press F9.

          FIELDS:

           1. Description.  A text description of the task.

           2. Label.  Optional.  A short (10 character) description of the
          task.  The label can be used for display purposes, but ^T make no
          other use of it.

           3. Number.  Optional.  Task id numbers or any other data desired
          by the user.  ^T makes no use of this field.

           4. Classification.  Optional, Choice field.  Select an
          appropriate classification from the table.

           5. Resource.  Required Choice field.  Link this task to a
          resource by selected a resource from the table.

           6. Project.  Optional Choice field.  If this task is to be
          linked to a project, select a project from the table.  Note that
          if no projects have yet been entered, the cursor will skip over
          this field.

           7. Chargeback.  Optional.  This field is intended for users who
          need to keep track of chargeback information.  ^T does not make
          use of this field.

           8. Priority.  Enter a priority from 0 to 99.  The lower the
          number, the higher the priority (more important).  The higher the
          number, the lower priority (less important).  The default is 50.
          If tasks of lower priority are moved to outline positions
          preceding tasks of higher priority, Priority Conflicts result.

           9. Commit Date.  If you wish to be warned if a task's calculated
          End Date is later than a specific target date, enter the target
          date in this field.  If the End Date of a task is later than the
          Commit Date, a Commit Date Conflict results.

          10. Adjust Working Hrs?.  Yes/No field.  Should the Scheduled
          Task Efficiency factor from the resource be used to adjust
          working hours to calendar duration hours?  Under normal
          circumstances this should be left to the default of YES.




                                        - 20 -




          However, some types of tasks should be set to NO.  For example,
          if this task is a trip that is going to last 3 days (or 24
          working hours),  the calendar duration is equal to working hours.

          11. Date Entered.  Defaults to the current system date, but can
          be changed to any date.  The Date Entered is used to calculate
          the Age of the task.

          12. Est. Working Hours.  The estimated number of working hours
          required to complete the task.  Once the task record is entered,
          this number cannot be changed.













































                                        - 21 -






                                                         DATA ENTRY SCREENS
                                                        TASK DETAILS (EDIT)


          PURPOSE: Edit an existing task.

          ACCESS: With the outline pointer positioned on an existing task,
          press Enter, or Select Edit from the main menu and Task from the
          edit menu.

          FIELDS:

           1. Description.  A text description of the task.

           2. Label.  Optional.  A short (10 character) description of the
          task.  The label can be used for display purposes, but ^T makes
          no other use of it.

           3. Number.  Optional.  Task id numbers or any other data desired
          by the user.  ^T makes no use of this field.

           4. Classification.  Optional, Choice field.  Select an
          appropriate classification from the table.

           5. Resource.  Required Choice field.  Link this task to a
          resource by selected a resource from the table.  If the resource
          is changed, the task will be reassigned to the new resource and
          automatically moved.

           6. Project.  Optional Choice field.  If this task is to be
          linked to a project, select a project from the table.  Note that
          if no projects have yet been entered, the cursor will skip over
          this field.  If the project is changed, the task will be
          reassigned to the new project.

           7. Chargeback.  Optional.  This field is intended for users who
          need to keep track of chargeback information.  ^T does not make
          use of this field.

           8. Priority.  Enter a priority from 0 to 99.  The lower the
          number, the higher priority (more important).  The higher the
          number, the lower priority (less important).  The default is 50.
          If tasks of lower priority are moved to outline positions
          preceding tasks of higher priority, Priority Conflicts result.

           9. Act. Working Hours.  Periodically enter the actual time spent
          working on this task.  It is critical that the number you enter
          is the actual working hours, not the duration or span of time.
          Entering data in this field causes the task to become Active (see
          below).  If either Act. Working Hours or O.T. Working Hours are




                                        - 22 -




          entered, the Percent Complete is required.

          10. O.T. Working Hours.  Enter the overtime hours spent working
          on this task.  ^T does not apply special cost rates to overtime.
          The field is included so that you may keep track of the overtime
          hours.  To determine the total hours worked on a task, ^T simply
          adds Act. and O.T. hours.  If either Act. Working Hours or O.T.
          Working Hours are entered, the Percent Complete is required.

          11. Percent Complete.  Enter an estimate of the percentage of the
          total task that is already completed.  If Percent Complete is
          entered, the Act. Working Hours and/or O.T. Working hours must be
          entered.

          12. Commit Date.  If you wish to be warned if a task's calculated
          End Date is later than a specific target date, enter the target
          date in this field.  If the End Date of the task is later than
          the Commit Date, a Commit Date Conflict results.

          13. Adjust Working Hrs?.  Yes/No field.  Should the Scheduled
          Task Efficiency factor from the resource be used to adjust
          working hours to calendar duration hours?  Under normal
          circumstances this should be left to the default of YES.
          However, some types of tasks should be set to NO.  For example,
          if this task is a trip that is going to last 3 days (or 24
          working hours),  the calendar duration is equal to working hours.

          14. Status.  Type 'A' to make the task ACTIVE, or 'I' to make it
          INACTIVE.  When Act. or O.T. hours are entered, the task
          automatically becomes ACTIVE.  Task status is used to determine
          Age Conflicts.  If a task's age exceeds the Age Warning Level, it
          will be considered a conflict only if it is in ACTIVE status.

          15. Actual Completion.  Enter the date that the task was actually
          completed.

          16. Date Entered.  Non-entry.  The date the task was entered into
          ^T.

          17. Est. Working Hours.  Non-entry.  The estimated number of
          working hours required to complete the task.

          18. Adj Hrs. Remaining.  Non-entry, calculated.  This represents
          the number of hours remaining to complete the task, adjusted to
          represent duration.  See CALCULATIONS, ADJUSTED HOURS for an
          explanation of the calculation.

          19. Age (in Cal. Days).  Non-entry, calculated.  The number of
          days from the date the task was entered into ^T to today's date.
          The age is actual calendar days, including non-working days.

          20. Est. Start.  Non-entry.  The start date of the task.  See




                                        - 23 -




          CALCULATIONS, TASK START AND END DATES.

          21. Est. End.  Non-entry.  The end date of the task.  See
          CALCULATIONS, TASK START AND END DATES.

          22. Predicted Cost.  Non-entry, calculated.  The cost of the
          project based on the original estimated number of hours to
          complete it.  See CALCULATIONS, TASK COSTS.

          23. Incurred Cost.  Non-entry, calculated.  The cost of the
          project based on the number of Act. and O.T. hours actually
          worked so far.  See CALCULATIONS, TASK COSTS.

          24. Est. Final Cost.  Non-entry, calculated.  The estimated final
          cost of the project derived from the number of Act. and O.T.
          hours actually worked so far and the percentage complete.  See
          CALCULATIONS, TASK COSTS.


                                                         DATA ENTRY SCREENS
                                           TASK FIELDS DISPLAYED IN OUTLINE


          PURPOSE: Configure the display of task records in the screen
          outline and in reports.

          ACCESS: Select Configure from the main menu and Task Fields from
          the configure menu.

          FIELDS:

          All fields are Yes/No fields.  There is a matching field for each
          field in a task record, including derived non-entry fields.  If a
          YES appears in the fields, that field will be displayed in the
          outline.  If NO, the field is not displayed.





















                                        - 24 -






                                                         DATA ENTRY SCREENS
                                                        VIDEO CONFIGURATION


          PURPOSE: Configure the video display for color or monochrome and
          customize colors.

          ACCESS: Select Configure from the main menu and Video from the
          configure menu.

          FIELDS:

          1. Mode.  Type 'C' to select the color table and 'M' to select
          the monochrome table.

          2. FGND.  Choice field.  For each area, choose a foreground color
          from the table.

          3. BGND.  Choice field.  For each area, choose a background color
          from the table.

          4. BRIGHT.  Yes/No field.  Determines if the foreground color is
          hi intensity.

          5. BLINK.  Yes/No field.  Determines if the character should
          blink.




























                                        - 25 -






                                                                      FILES
                                                                    ARCHIVE
                                                                       .RCV


          PURPOSE: To store deleted task and project records.  IMPORTANT
          NOTE: At present, ^T only archives records in this file.  It
          provides no facility for accessing those records once they're
          stored.  Depending on demand, future versions may provide access
          facilities.

          NAMING CONVENTION: When you delete a task or a project and
          indicate that it is to be archived, a file is created (or opened
          if it already exists) with a name identical to the task outline
          file name but with a .RCV extension.  For example, if your task
          outline is called MYTASKS.TSK, the associated archive file will
          be MYTASKS.RCV.

          RECORD LAYOUT:

          Archived task and project records are added to the file in the
          order in which they are deleted from the task outline.  The first
          character of each record is either a 'T' for a task record or a
          'P' for a project record.  Each record ends with a CRLF sequence,
          so records may be read in "line" or text mode.

          The archive task record layout is as follows:

               FIELD                 LENGTH  START   END    FORMAT
               --------------------  ------  -----  -----   ----------
               Identifier               1       1      1    "T"
               Description             40       2     41    text
               Label                   10      42     51    text
               Number                  10      52     61    text
               Classification          15      62     76    text
               Resource                10      77     86    text
               Project                 10      87     96    text
               Chargeback              10      97    106    text
               Priority                 2     107    108    99
               Act. Working Hours       7     109    115    9999.99
               O.T. Working Hours       7     116    122    9999.99
               Percent Complete         3     123    125    999
               Commit Date              8     126    133    MM/DD/YY
               Adjust Work Days         1     134    134    "Y" or "N"
               Status                   1     135    135    "A" or "I"
               Actual Completion        8     136    143    MM/DD/YY
               Date Entered             8     144    152    MM/DD/YY
               Est. Working Hours       7     153    159    9999.99
               Adj. Hours Remaining     7     160    166    9999.99
               Age                      3     167    169    999




                                        - 26 -




               Est. Start               8     170    177    MM/DD/YY
               Est. End                 8     178    185    MM/DD/YY
               Predicted Cost           8     186    193    99999.99
               Incurred Cost            8     194    203    99999.99
               Est. Final Cost          8     204    211    99999.99
               Resource name           40     212    251    text
               Project Description     40     252    291    text
               CRLF                     2     292    293    CRLF

          The archive project record layout is as follows:

               FIELD                 LENGTH  START   END    FORMAT
               --------------------  ------  -----  -----   ----------
               Identifier               1       1      1    "P"
               Description             40       2     41    text
               Label                   10      42     51    text
               Number                  10      52     61    text
               Commit Date              8      62     69    MM/DD/YY
               Est Start Date           8      70     77    MM/DD/YY
               Est End Date             8      78     85    MM/DD/YY
               Act Completion           8      86     93    MM/DD/YY
               Predicted Cost           8      94    101    99999.99
               Incurred Cost            8     102    109    99999.99
               Est. Final Cost          8     110    117    99999.99
               CRLF                     2     118    119    CRLF


                                                                      FILES
                                                                 ASCII DATA
                                                                       .ASC


          PURPOSE: An ASCII data file is created when you print one of the
          reports and specify ASCII Data as the output device.

          NAMING CONVENTION: The ASCII Data file name is taken from the Out
          File field in Print Options and the extension .ASC is
          automatically appended.

          CONTENTS: There is one record in the file for each task in the
          outline.  If the outline is in Resource orientation (Rearrange-
          Resource), the task data is preceded by the resource data for
          that task.  If outline is in Project orientation (Rearrange-
          Project), the resource and task data is preceded by the project
          data for that task.  Only the fields displayed on the screen are
          included in the ASCII data file.  Each field is formatted in the
          file as it is formatted on the screen.  As on the screen, there
          is a single blank space separating each field.  Finally, each
          record is terminated with a CRLF sequence, so the records may be
          read by another program in "line" or text mode.






                                        - 27 -






                                                                      FILES
                                                              CONFIGURATION
                                                                     ^T.CFG


          PURPOSE: Holds current configuration data for all the screens
          that are accessed via Configuration on the main menu except
          Printer Driver Configurations.

          NAMING CONVENTION: The configuration file is named ^T.CFG.


                                                                      FILES
                                                             PRINTER BUFFER
                                                                  PRINT.BUF


          PURPOSE: All print output intended for either the Printer or the
          Screen is written into this file before being sent to the device.

          NAMING CONVENTION: The printer buffer file is named PRINT.BUF.

          CONTENTS: The PRINT.BUF file contains the complete output from
          the printing of a report, including printer control codes if the
          output is intended for a printer.  At present, ^T does not print
          multiple copies of a report.  However, after printing a report,
          you can shell to DOS (using File-DOS Shell) and use the DOS Print
          (e.g. PRINT PRINT.BUF) or Type (e.g TYPE PRINT.BUF > LPT1)
          commands to send the file repeatedly to the printer.


                                                                      FILES
                                                             PRINTER DRIVER
                                                                       .DRV


          PURPOSE: Store configuration info and control codes for a
          printer.

          NAMING CONVENTION: Each printer driver is stored in an separate
          file with a user-specified file name and the automatically
          appended extension .DRV.












                                        - 28 -






                                                                      FILES
                                                                 PRINT FILE
                                                                       .PRN


          PURPOSE: A print file is created when you print one of the
          reports and specify Print File as the output device.

          NAMING CONVENTION: The print file name is taken from the Out File
          field in Print Options and the extension .PRN is automatically
          appended.

          CONTENTS: A print file contains the output of a report formatted
          as though for a printer but containing no control codes.


                                                                      FILES
                                                               TASK OUTLINE
                                                                       .TSK


          PURPOSE: Stores all information for a task outline, including the
          custom calendar information.

          NAMING CONVENTION: Each task outline is given a user specified
          filename (via the File-Rename function).  The extension .TSK is
          automatically appended.



























                                        - 29 -






                                                                   KEYBOARD
                                                           MAIN SCREEN KEYS


               MOVEMENT IN OUTLINE

                    Up Arrow    - Up one line
                    Down Arrow  - Down one line
                    Left Arrow  - Scroll left
                    Right Arrow - Scroll right
                    Page Up     - Up 21 lines
                    Page Down   - Down 21 lines
                    Ctl-Home    - Go to line 1
                    Ctl-End     - Go to last line
                    Enter       - Edit current line
                    
               USING MENUS
                    Select menus - press highlighted letter
                                   alone or in combination
                                   with Alt key
                    Select menu item - press highlighted
                                   letter or press Enter to
                                   select current item
                    Left Arrow   - Show menu to left
                    Right Arrow  - Show menu to right
                    Up Arrow     - Move up one menu item
                    Down Arrow   - Move down one menu item
                    Enter        - Select current item
                    Esc          - Return to outline mode

               OTHER

                    Esc - Quit from program
                    F1  - Help




















                                        - 30 -






                                                                   KEYBOARD
                                                            DATA ENTRY KEYS


               FIELD-TO-FIELD MOVEMENT

                    Up Arrow    - Previous field
                    Down Arrow  - Next field
                    Tab         - Next field
                    Backtab     - Previous field
                    Page Up     - First field
                    Page Down   - Last field
                    Enter       - Next field
                    
               FIELD EDITING

                    Left Arrow  - Previous character
                    Right Arrow - Next character
                    Del         - Delete current character
                    Ins         - Toggle insert/typeover modes
                    Backspace   - Delete previous character
                    Home        - Beginning of field
                    End         - End of field
                    + or -      - Add/subtract working days

               CHOICE TABLE MOVEMENT

                    Up Arrow   - Next choice
                    Down Arrow - Previous choice
                    Enter      - Select choice

               OTHER

                    F1  - Help
                    F2  - End editing, process changes
                    Esc - Quit editing, discard changes


















                                        - 31 -






                                                                   KEYBOARD
                                                          QUICK ACCESS KEYS


               F1  - Help
               F2  - End editing and proceed (during data-entry only)
               F3  - Load new task outline file (same as File-Load)
               F4  - Save outline file to disk (same as File-Save)
               F5  - Perform recalc on outline (same as File-Calc)
               F6  - Update all resources to current date (same as Edit-
                     Update)
               F7  - Move current task (same as Rearrange-Move)
               F8  - Print outline report (same as Print-Outline)
               F9  - Add a new task (same as Add-Task)
               F10 - Delete current task (same as Delete-Task)







































                                        - 32 -






                                                                MAIN SCREEN


          Below is a schematic view of the ^T main screen.



                                  .---- 1. Main Menu
                                  |                    2. Help Key ---,
                                  |                                   |
           File Edit Add Delete Rearrange Configure Print          F1 Help
          +--------------------------filename-----------------------------+
          | Resource 1                  |                                 |
          |     Task 1                  |                                 |
          | PCA Task 2                  `--- 3. Current Filename          |
          | |                                                             |
          | `--- 4. Conflicts                                             |
          |                                                               |
          |                                                               |
          |                    5. Outline Area                            |
          |                                                               |
          |                                                               |
          |                                                               |
          +---------------------------------------------------------------+
           R50 P100 T500 | date/time | Conflict | Calc | Num | Caps | Ins
                 |             |           |        |            |
                 |             |           |        |            |
            6. Capacity        |           |   9. Recalc   10. Toggle Key
                               |           |      Pending      Indicators
               7. Current Date And Time    |
                                           |
                                 8. Conflict Warning

          1. Main Menu.  Top level menu items.  When selected, each
          displays a drop-down menu.  Main menu items can be selected by
          typing the first letter of the menu name, either alone or in
          combination with the Alt key.  For example, to select the File
          menu, press either F or Alt-F.

          2. Help Key.  To obtain help, press F1.  The help system in
          version 1.0x is made up of several screens documenting the use of
          the keyboard.

          3. Current Filename.  If no file has been selected, the filename
          will appear as '????????'.  Otherwise, the full pathname of the
          current file is displayed.

          4. Conflicts.  P = Priority conflict, C = Commitment date
          conflict, A = Age conflict.





                                        - 33 -




          5. Outline Area.  Area of the screen in which the task outline is
          displayed.

          6. Capacity.  Shows the space remaining for new resources (R),
          projects (P), and tasks (T).  ^T's maximums are 50 resources, 100
          projects, and 500 tasks.

          7. Current Date And Time.  Shows the day of the week, the current
          date, and the current time according to the system clock.

          8. Conflict Warning. If the default colors have not been changed,
          the word Conflict is displayed in black if there are no Priority,
          Commitment Date, or Age conflicts or violations.  It will become
          bright white when a conflict exists for any task in the outline.

          9. Recalc Pending.  If ^T is configured to Manual Recalc, and
          changes were made that require recalculation, the word Calc will
          display in bright white.

          10.  Toggle Key Indicators.  Whenever the Caps Lock, Num Lock, or
          Insert keys are activated the corresponding indicator will light
          up.


                                                                       MENU
                                                                        ADD


          Add-Task.  Add a new task after the current task.  Tasks cannot
                     be added until at least one resource has been added.

          Add-Resource.  Add a new resource after the current resource.

          Add-Project.  Add a new project.






















                                        - 34 -






                                                                       MENU
                                                                  CONFIGURE


          Configure-Default Calendar.  Configure the default calendar.  The
                    default calendar is used to "seed" the custom calendar
                    for each new task outline.

          Configure-Classifications.  Configure the table of task     
                    classifications.

          Configure-General Defaults.  Configure general defaults.

          Configure-Setup Printer.  Configure the current printer driver or
                    add a new driver.

          Configure-Task Fields.  Setup the task fields that are displayed
                    in the outline.

          Configure-Resource Fields.  Setup the resource fields that are
                    displayed in the outline.

          Configure-Project Fields.  Setup the project fields that are
                    displayed in the outline.

          Configure-Video.  Configure color or monochrome mode and    
                    customize colors.



























                                        - 35 -






                                                                       MENU
                                                                     DELETE


          Delete-Task.  Delete the current task.  After selecting this
               function, you'll be given a choice to Archive or Discard the
               record.  Archive results in the record being written to the
               archive (.ARC) file, Discard results in the record simply
               being erased.  If the task is assigned to the project, a
               warning is given.  If the task is deleted, its data is no
               longer included in the project summaries.

          Delete-Resource.  Delete the current resource.  A resource can
               only be deleted when there are no tasks assigned to it.

          Delete-Project.  Delete the current project.  A project record
               can be Archived or Discarded.  Archive results in the record
               being written to the archive (.ARC) file, Discard results in
               the record simply being erased.  If the project has tasks
               assigned to it, a warning will be given.  If the record is
               deleted anyway, the project summary is lost but there is no
               other affect on the associated tasks.


                                                                       MENU
                                                                       EDIT


          Edit-Task Data.  Edit the current task.

          Edit-Resource Data.  Edit the current resource.  If a task is
               currently highlighted, the resource associated with that
               task will be edited without having to move the pointer to
               that resource.

          Edit-Project Data.  Edit the current project.  If a task is
               currently highlighted, and that task is linked to a project,
               the linked project will be edited.

          Edit-File Description.  Edit the current file description, path,
               and filename.

          Edit-Calendar.  Edit the custom calendar that is associated with
               the current task outline.

          Edit-Update Resources.  This function results in the Start Date
          for each resource being set to the current date.  This is
          typically used when task data is updated on a regular basis (e.g.
          after a weekly status meeting) and all the resources need to be
          changed.




                                        - 36 -






                                                                       MENU
                                                                       FILE


          File-Load.  Load a new task outline.

          File-New.  Clear the current task outline from memory.

          File-Save.  Save the current task outline to disk.  If the
               current outline has not yet been named, do a File-Rename and
               then save again.

          File-Rename.  Give the current outline a new description, path,
               or filename.

          File-Calc.  If the system is configured to manual recalc mode,
               this function will recalculate the outline.

          File-DOS Shell.  Passes control to DOS.  When finished with DOS,
               typing 'exit' and pressing return will give control back to
               ^T.

          File-Pgm Info.  Display an informational screen.  The program
               version number is found on this display.

          File-Exit.  Quit from ^T.




























                                        - 37 -






                                                                       MENU
                                                                      PRINT


          Print-Outline.  Print the outline exactly as it appears on the
               screen.

          Print-Resource Assignments.  Print separate reports showing only
               the tasks for a given resource.  You have a choice to select
               am individual resource or have all resources printed.  If
               you select 'All' resources, each one will be started on a
               new page.  This report is intended to produce a task
               assignment list for distribution to individual resources.

          Print-Project Assignments.  Print separate reports showing only
               the resources and tasks for a given project.  You have a
               choice to select am individual project or have all projects
               printed.  If you select 'All' projects, each one will be
               started on a new page.

          Print-Cancel Print Job.  Printing in ^T takes place in
          background.  To cancel the print job, select this function.  Note
          that this does not erase data already in the printer's buffer.































                                        - 38 -






                                                                       MENU
                                                                  REARRANGE


          Rearrange-Move Task.  After selecting this function, the system
               is placed in "move" mode.  Note the message in the lower
               left corner.  Use the arrow keys to move the task up or down
               in the outline.  Tasks can be moved across resource
               boundaries but not across project boundaries.
               Recalculations take place as the task is moved.  Move is
               much quicker in manual calc mode.  To end move mode, press
               Esc  or Enter.

          Rearrange-Copy Task.  Make a copy of the current task.  ^T
               displays an Add Task screen in which all data is initialized
               to the values of the current task.

          Rearrange-Hide Tasks.  Hide tasks from being displayed in the
               task outline.  This would typically be done to allow quick
               movement between resources or projects.

          Rearrange-Display Tasks.  Redisplay tasks in the outline after
               they were hidden.

          Rearrange-Resource Outline.  Place the outline into Resource
               orientation.  In this view, resources are the top level of
               the outline, with tasks immediately below.  Projects are not
               displayed.

          Rearrange-Project Outline  Place the outline into Project
               orientation.  In this view, projects are the top level of
               the outline, with resources and the next level, and tasks
               below resources.



                                                                    REPORTS
                                                FIELDS DISPLAYED IN REPORTS


          The fields displayed for task, resource, and project records in
          all reports is determined by the configuration settings.  To
          customize reports showing different fields use the Configuration
          menu and Task Fields, Project Fields, and Resource Fields
          functions to turn fields on and off.









                                        - 39 -






                                                                 APPENDIX A
                                                        REQUIREMENTS/LIMITS


          Maximum Tasks............................500
          Maximum Resources.........................50
          Maximum Projects.........................100

          Free Memory Required For Maximum Items...384 KB

          If less memory is available, ^T will reduce the maximum number of
          tasks in an attempt to fit.  If fewer than 25 tasks will fit in
          available space, ^T will not run.  The counters in the lower left
          corner of the main screen report how many resources (R), projects
          (P), and tasks (T) can be added.

          Minimum Disk/File Requirements

               Main program (^T.EXE)...............192 KB
               Printer Driver (.DRV)...............  8 KB

          Additional disk space will be required for task outlines, archive
          files, and a print buffer.  These files will tend to grow in
          size, but an additional 64K of space will provided for an average
          application.

          ^T can run very well from a 360KB floppy disk.



























                                        - 40 -






                                                                 APPENDIX B
                                                             ERROR MESSAGES


          Most ^T error messages are clearly stated and occur under
          circumstances that make solutions obvious.  However the following
          messages might not be so clear and require additional
          explanation.

          AT LEAST ONE RESOURCE MUST BE ADDED FIRST

               Tasks cannot exist in ^T without being related to a
               resource.  Therefore, at least one resource record must be
               added before you can add a task.

          CONFIGURATION FILE ^T.CFG NOT FOUND

               ^T looks for the configuration file in the current
               directory.  Make sure that the ^T directory is the current
               directory and that the ^T.CFG file is in that directory.

          DOS SHELL FAILED

               This message occurs when there is insufficient free memory
               to load a secondary command processor.  You cannot shell to
               DOS, but otherwise the operation of ^T is not affected in
               any way.  No data has been lost and you can continue
               working.

          ERROR ON CALLOC IN FUNCTION PUSH_WINDOW

               There is insufficient free memory to create a buffer to
               store a window area.  Free up additional memory and run ^T
               again.

          FILE TOO LARGE FOR AVAILABLE MEMORY

               The number of tasks, resources, and/or projects stored in
               the outline fit cannot fit in available memory.  This can
               occur if the outline was created under maximal memory
               conditions, and now ^T is being run under more restrictive
               memory conditions.  Free up additional memory and run ^T
               again.

          INVALID FILENAME

               The filename entered is an invalid DOS filename.  The
               filename cannot contain the characters listed below:

               . \ " / [ ] : | < > + = ; , space




                                        - 41 -





          LABEL IS REQUIRED

               For both projects and resource the label field is a required
               field.  To link tasks to resources and/or projects, ^T
               requires the label (presented via a choice table) to be
               entered in the appropriate field in the task records.

          LABEL MUST BE UNIQUE

               Project and resource labels must be unique within the record
               type.  In other words, each resource label must be unique
               among all resource labels, each project label must be unique
               among all project labels.  A resource and a project can both
               have the same label.

          LIST MEMORY ALLOCATION FAILED

               Insufficient memory is available for ^T to allocate required
               memory buffers.  Free up additional memory and run ^T again.

          MUST HIGHLIGHT TASK TO BE COPIED

               Before a task can be copied, the outline pointer must be
               positioned on an existing task.

          NO CONNECTION TO EXISTING PROJECT

               You attempted to edit a project while the pointer was
               positioned on a task that is not linked to an project.
               Either edit the task record to link to a project, or do a
               Rearrange-Project Outline to get a clearer view of which
               tasks are connected to projects.

          NO FILES ARE STORED

               No outline files have yet been created and saved.  Create an
               outline by (1) editing the calendar, (2) adding some
               resources, (3) adding some tasks, (4) performing a File-
               Rename, (5) and saving the file.  Also, it is possible that
               the are no outline files in the path you specfied.  Make
               sure the path is correct.

          NULL POINTER T_FILE.C: OPEN_READ_PRINT_FILE()

               ^T is having a problem accessing the PRINT.BUF file.  The
               most likely causes are (1) insufficient disk space, or (2)
               shelling to DOS and tampering with the PRINT.BUF file before
               a report is finished printing.

          PROJECT LIST FULL





                                        - 42 -




               The maximum number of projects has already been added.  The
               maximum number of projects is 100.  Try deleting some unused
               or obsolete projects.  Also, if a job is essentially made up
               of a single task, do not use a project record for that job.

          PROJECT MEMORY ALLOCATION FAILED

               Insufficient memory is available for ^T to allocate required
               memory buffers.  Free up additional memory and run ^T again.

          RESOURCE LIST FULL

               The maximum number of resources has already been added.  The
               maximum number of resources is 50.

          RESOURCE LIST IS EMPTY

               No resources have yet been added.  You must add a resource
               before you can edit one.

          RESOURCE MEMORY ALLOCATION FAILED

               Insufficient memory is available for ^T to allocate required
               memory buffers.  Free up additional memory and run ^T again.

          RESOURCE STILL HAS TASKS ASSIGNED

               A resource cannot be deleted while there are still tasks
               assigned to it.  Either delete the tasks or reassign them to
               another resource.

          RESOURCE TABLE MEMORY ALLOCATION FAILED

               Insufficient memory is available for ^T to allocate required
               memory buffers.  Free up additional memory and run ^T again.

          TASK DURATION EXCEEDED INTERNAL CALENDAR CAPACITY

               The ending date of a task will be later than the last date
               in ^T's internal calendar.  The internal calendar is 5 years
               long, starting on January 1 of the year of the earliest
               start date of any resource, and ending on December 31 of the
               fourth following year.

          TASK LIST FULL

               The maximum number of tasks has already been added.  The
               maximum number of tasks is 500.  However, if available
               memory is restrictive, ^T may not have enough room for 500
               tasks.  When starting ^T, if some number less than T:500 is
               shown in the lower left corner, you may be able to gain more





                                        - 43 -




               task space by freeing up additional memory and running ^T
               again.

          TASK MEMORY ALLOCATION FAILED

               Insufficient memory is available for ^T to allocate required
               memory buffers.  Free up additional memory and run ^T again.

          WARNING: TASK IS LINKED TO A PROJECT

               You are attempting to delete a task that is linked to a
               project.  This is a warning only.  If you proceed to delete
               the task, that task's data will no longer be including in
               the project's totals.

          WARNING: THERE ARE STILL TASKS LINKED TO THIS PROJECT

               You are attempting to delete a project that still has tasks
               attached.  This is a warning only.  If you proceed to delete
               the project, all project data will be lost, and any linked
               tasks will be automatically unlinked from the project.
               Other that being unlinked, the tasks records will not be
               affected in any way.

































                                        - 44 -






                                                                 APPENDIX C
                                                             VIDEO HANDLING


          ^T attempts, at startup, to determine the type of video adapter
          attached to the system.  If ^T detects the IBM Monochrome/Printer
          Adapter (MPA), the base address for direct screen accesses is set
          to segment hex B000.  Any other adapter detected (including CGA,
          EGA, VGA, or unknown) will result in segment hex B800 being used.

          ^T uses BIOS Video mode 7 with MPA systems, and mode 3 on all
          other systems.

          ^T can be configured as to color by selecting Configure from the
          main menu and Video from the Configure menu.  With the cursor in
          the Mode field, type 'C' to select the color table, and 'M' to
          select the monochrome table.  The colors can then be individually
          customized.




































                                        - 45 -






                                                                 APPENDIX D
                                                             FREEING MEMORY


          There are several ways to free memory.  Here is a list of things
          to look for.

          1. Remove RAM-resident programs.  These could include keyboard
          macro programs, DOS shells, printer utilities, terminal
          emulators, desktop organizers, etc.  Make sure that what is being
          loaded is really needed.  Remember that for each program loaded,
          regardless of size, DOS also reserves space for the Program
          Segment Prefix (256 bytes) and a copy of the environment
          (anywhere from 127 bytes to 32,767 bytes).  Check your
          AUTOEXEC.BAT file.  You might be surprised to find that a RAM-
          resident program you were "just checking out" a few months ago is
          still being loaded.

          2. Check your CONFIG.SYS file for any unnecessary device drivers.
          Many users have obsolete device drivers installed.  Also, don't
          set variables like BUFFERS, FILES, and STACKS to extremes.  Set
          them to what you need, and no more.

          3. Keep your environment size down to what is required.  Keep
          environmental variables as small as possible.  For example, don't
          have a PATH set to 20 directories when you only need it set to 4
          or 5.

          4. If you're running ^T from a menu system, try running it from
          DOS instead.

          5. If ^T was running fine and suddenly there's not enough memory
          to run, you may have loaded a RAM-resident program in the
          interim, or you may have forgotten that you are shelled out of a
          program that is still in memory (I do this frequently).

          6. If you shell out of ^T, type EXIT to return.  DO NOT run ^T a
          second time.  Also, when shelled out of any program, it is
          generally unwise to change files or run RAM-resident programs.















                                        - 46 -