E A S Y  P R O J E C T (TM)

                                USER MANUAL

                 A Project Management and Tracking System
             for the I.B.M. and Compatible Personal Computers



             (c) Copyright 1987,1988,1989,1990 Parcell Software
                            All Rights Reserved
























                             Parcell Software
                               P.O. Box 165
                          Geneva, Il  60134  U.S.A








(c) Copyright 1987,1988,1989,1990  Parcell Software
All Rights Reserved Worldwide
Printed in the United States of America

Parcell Software
P.O. Box 165
Geneva, Il  60134  U.S.A.

Voice:   (708) 232-6328   (9:00 a.m. - 5:00 p.m. Central Time)
BBS:     (708) 232-6339
CompuServe:  72250,1356

Trademarks

Easy Project is a trademark of Parcell Software
I.B.M. is a registered trademark of the I.B.M Corporation.
dBASE III is a registered trademark of Ashton-Tate, Inc.

License Agreement

Easy Project is a Shareware program.  It is not free.

Easy Project is copyrighted software owned by Parcell Software.
Continued use requires a registration fee of $49.00. Registration
covers use on one PC only.  Multiple copies of Easy Project must
be purchased for use on multiple PC's.  Quantity discounts and
site licenses available.

      All licensed users receive:

           Latest version with Shareware screen disabled
           User Manual
           Notification of updates
           Free technical support
           Special BBS access

You are encouraged to copy and share this program with other
users. When sharing this program, all files and documentation
must be distributed without any alteration.  No fee can be
charged for any copying or distribution except for a nominal fee
to defray expenses.

Hardware Requirements

I.B.M. PC/XT/AT/PS2 or 100% Compatible with at least 384K RAM and
any type monitor.  A hard disk is recommended but not necessary.
Over 40 different printers are supported.  If your particular
printer is not listed on the printer configuration screen, please
contact us.

Disclaimer

Parcell Software specifically disclaims any warranty, either
expressed or implied, including but not limited to the implied
warranties of merchantability and fitness for a particular use.
In no event shall Parcell Software be liable for any special,
consequential, or other damages, including loss of profit arising
out of the use of this program.

                 T A B L E  O F  C O N T E N T S




Introduction . . . . . . . . . . . . . . . . . . . . . . . . .  3

System Software Requirements . . . . . . . . . . . . . . . . .  4

Installation . . . . . . . . . . . . . . . . . . . . . . . . .  5

Starting Easy Project. . . . . . . . . . . . . . . . . . . . .  5

Keyboard Control . . . . . . . . . . . . . . . . . . . . . . .  6

Main Menu. . . . . . . . . . . . . . . . . . . . . . . . . . .  7

Using Easy Project . . . . . . . . . . . . . . . . . . . . . .  8

Project Parameters . . . . . . . . . . . . . . . . . . . . . .  9

Resource Maintenance . . . . . . . . . . . . . . . . . . . . . 11

Task Parameters. . . . . . . . . . . . . . . . . . . . . . . . 13

Quick-Input. . . . . . . . . . . . . . . . . . . . . . . . . . 17

Automatic Schedule Generation. . . . . . . . . . . . . . . . . 18

Gantt Chart. . . . . . . . . . . . . . . . . . . . . . . . . . 19

Reports. . . . . . . . . . . . . . . . . . . . . . . . . . . . 21

Utilities. . . . . . . . . . . . . . . . . . . . . . . . . . . 23

Conclusion . . . . . . . . . . . . . . . . . . . . . . . . . . 25

                    E A S Y  P R O J E C T (TM)                          3


Introduction

Easy Project is a tool to assist anyone who manages.  Easy
Project encourages the manager to define a project into a series
of phases and tasks.  Easy Project facilitates the planning,
scheduling and tracking of all types of projects.  You the
manager, plan the activities or tasks in a top/down outline
fashion.  The Gantt chart then displays the project graphically
by using time bars which span the time period of each task.

Easy Project features:

       Ability to create projects with 2000 tasks

       Gantt charts detailing planned vs. actual progress

       Automatic scheduling

       Critical path calculation

       Extensive reporting

       Context sensitive HELP

       dBASE file compatibility

A sample project is provided to assist in learning and using Easy
Project.  Use the project number of 'EASY' (all caps) to access
the sample project data.


==OPENING SCREEN==

System Software Requirements                                              4

For the purpose of this documentation, it is assumed the user has
a 'working' knowledge of DOS.  The user should be able to copy
and backup files, create directories and edit text files.  Please
consult your DOS manual with questions regarding any of these
functions.

CONFIG.SYS File (sample is included)

     A CONFIG.SYS file must be in the root directory of your hard
     disk or on your DOS system floppy.  This file must contain
     the following two records:
                       BUFFERS = 15
                       FILES = 25
     These values are minimum values. Consult your DOS manual for
     further information regarding the CONFIG.SYS file.

     To activate changes made to the CONFIG.SYS file, re-boot
     your PC!


First Time Installation

Hard Disk

     1.  Make a backup copy of your Easy Project disk.
     2.  Place your backup copy in drive A and type:
          INSTALLH <enter>

     This installation procedure will create a sub-directory on
     your hard disk of \EP and copy the necessary files.

     NOTE:  This process assumes drive C is your hard disk.  If
     this not the case, edit the INSTALLH.BAT file accordingly.


2 Floppy System

     1.  Make a backup of your Easy Project disk.
     2.  Place the backup copy in drive A and a blank formatted
     disk in drive B, type:  INSTALLF <enter>

     This process will copy all necessary data files to drive B
     and keep system files on drive A.  Label the disk in drive A
     "EP System" and the disk in drive B "EP Data".






Upgrading From Prior Versions                                             5

To upgrade Easy Project from a 2.X version, follow these steps:

     1.  Backup all current Easy Project files
     2.  RENAME EPPROJ.DBF EP2PROJ.DBF
         RENAME EPPLAN.DBF EP2PLAN.DBF
         RENAME EPRES.DBF  EP2RES.DBF
     3.  Install new files
     4.  COPY EP2RES.DBF EPRES.DBF
     5.  Start Easy Project (EP)
     6.  Choose Utilities option and Reindex Files
     7.  Choose Utilities option and Configure System
     8.  Choose Utilities option and Convert 2.0 Files

To upgrade from a version 3.X version, copy the EP.EXE, EPRES2.DBF,
EP.BAT, and EPRES2T.NTX files and from the Utilities Menu:

     1.  Choose Configure System and update accordingly
     2.  Choose the Rebuild option


Starting Easy Project

Hard Disk

     From the \EP directory, type:  EP <enter>

2 Floppy System

     With the EP System disk in drive A, the EP Data disk in
     drive B, and drive B as the default drive,type :   A:EP
     <enter>


NOTE:  The first time you execute Easy Project, choose the
Utilities option from the Main Menu.  From this menu, choose
Configure System and then Configure Printer and update
accordingly.

Possible Start-up Error Messages

     1.  Open Error(2) - One or more files is missing from your
     installed system.  Please check your original disk. (check
     .NTX and .DBF files)

     2.  Open Error(4) - Too many files are open.  Check your
     CONFIG.SYS file (see System Software Requirements).


Keyboard Control                                                         6

On most Easy Project data entry screens, the cursor can be
controlled in the following fashion:

     Key                    Result

     <--|      Proceeds to the next field.  When pressed while
               the cursor is in the last field of a screen, all
               data will be saved.

     PgDn      Exits the screen saving all changes.

     Esc       Exits the screen without saving any changes.

     Up Arrow  Moves cursor to previous field.

     Dn Arrow  Moves cursor to next field.

     <-        Moves cursor backward.

     ->        Moves cursor forward.

     F2        Displays program license and prints registration
               form.

     F5        Deletes current record while in Resource or Task
               Parameter screens.

     F9        Scrolls Gantt chart into the past.

     F10       Scrolls Gantt chart into the future.

Need Help?

At any time, help is available by pressing 'F1'.  Easy Project
will recognize what field or menu the request came from, and
then display the appropriate text.

Three fields will provide additional HELP when the F1 key is
pressed:

     Project Number:  Will list all active projects on file.

     Task Number:  Will list all tasks for a particular project.

     Resource:  Will list all resources for a particular project.




Main Menu                                                                7


The Main Menu permits access to your projects.  The desired
function can be chosen using either one of two methods:

     1.  Use the left or right arrow key to highlight the desired
     option and then press the <Enter> key

     2.  Press the capitalized letter of the desired choice (i.e.
     T=Task, O=repOrt)

The components of the Main Menu are:

               Project
               Create project numbers, project descriptions,
               phase descriptions and define holidays

               Resource
               Maintain resource data

               Task
               Maintain task data

               Quick-input
               Mass input for new tasks

               Schedule
               Schedule work plans automatically

               Gantt
               Produce Gantt charts detailing planned vs. actual
               project progress

               repOrts
               Generate reports including work plans, status
               reports and project summary reports

               Utilities
               Configure system and provides utility project
               handling

               sYstem
               Shell to DOS

               Exit
               Quit Easy Project


Using Easy Project - A Fast Start                                        8


Easy Project is designed for quick project creation.  After
spending a short time entering project data, Gantt charts and
reports can be produced by the manager.

Follow this process when creating a new project:

     1.  Choose 'Project' from the Main Menu and enter a project
     number, descriptions, phase descriptions and project
     holidays.

     2.  Choose 'Resource' from the Main Menu and enter resource
     data for the project.  Resources will be identified by
     assigning them a unique code.

     3.  Choose 'Task' from the Main Menu to enter and maintain
     tasks for the project. (See Notes On Entering Tasks)

     4.  If you want Easy Project to calculate a project
     schedule, choose 'Schedule' from the Main Menu. (See Notes
     on Automatic Scheduling)

     5.  At this point, Gantt charts and reports may be produced.

NOTE:  A sample project has already been established.  Use the
project number of 'EASY' (all caps) to view this project.


Maintaining an Existing Project


When initially starting the system, no project will be active.
To activate or retrieve a project, you will be prompted for the
project number the first time you try any Main Menu function -
except Gantt. To change projects, go to the 'Project' screen or
any report screen.

F1 Key

Remember to make use of Easy Project's context sensitive HELP
screens.  The F1 key can be pressed while in any part of the
system to provide quick support.




Project Parameters                                                        9


Easy Project has the ability to store data from several different
projects at one time.  Each of those projects may have different
base parameters.

Before entering task or resource data for a particular project,
certain parameters or criteria must be defined on the Project
Parameter screen.




==PROJECT PARAMETER SCREEN==








Project Number

     Every project must have its own unique project number.  This
     number is used to tell the system what project should be
     retrieved.  This number can be composed of any combination
     of characters or numbers (5 character maximum).

     NOTE:  Pressing the F1 key while on the project number field
     will provide a list of all active projects.

Project Name

     Use this field to identify the project.  This description
     will appear on all screens and reports.

Project Description

     To further define a project, use these fields.  The data
     entered here will print on all reports.




Phase Descriptions                                                       10

     For most projects, it is better to divide the project into
     smaller, more manageable phases.  An example of phases could
     be:

          1.  Lay foundation
          2.  Framing
          3.  Plumbing

     Easy Project permits 20 different phases to be defined for
     one particular project.  The descriptions entered here will
     appear on project summary reports.

Non-Schedule Days

     Twelve different dates may be entered as non-schedule days.
     These will be useful in scheduling holidays and vacations.

Weekends?

     If Saturday and Sunday are not to be used when scheduling,
     enter a 'N'.

     If weekend days are to be scheduled, enter a 'Y'.



Resource Maintenance                                                    11

Before tasks can be entered, resource information must be
established.  Resources consist of staff (employees, consultants,
etc.) or fixed type (materials, capital expenses, etc.).




==RESOURCE SCREEN==




Code

     Each resource must be assigned a unique identifier.  This
     identifier could be a name, initials or an account code.
     The identifier can be up to 6 characters and is
     alphanumeric.

     NOTE:  Pressing the F1 key while the cursor is on the
     Resource Code field, will display a list all resources
     assigned to this project.

Name

     Enter the full name or description of the resource.

Rate

     The charge rate for the resource. (optional)

Type

     Choose either Hourly, Daily, or Fixed.

Dept

     Enter a department code for the resource.  This code
     may be up to 3 characters and is alphanumeric.

     NOTE:  This is an optional entry but is needed to produce
     departmentalized reports.


Usage

     Use to identify how many hours this resource works in one
     day.  (not needed for Fixed types)

          Example:    8 = 8 hours/day
                      4 = 4 hours/day (part time)



Source                                                                   12

     An optional entry to further describe the resource.

          Example:    EMP = Employee
                      CON = Consultant

Note 1 & Note 2

     An optional entry to be used for any purpose.


Task Parameters                                                        13


Task definition is the heart of project management. Before
sitting down and entering task data, plan what logical order your
tasks will follow and if possible, divide your project into
phases. Once your data has been entered, refinement and
maintenance is easy.


==TASK PARAMETER SCREEN==




Task

     Enter the two digit phase number plus four digit task number
     for this task. Refer to 'Notes on Entering Tasks' for
     creating task numbers.

Item

     Each task can consist of numerous subordinate tasks or
     items.  Enter an item number in this field. (optional)

Network

     Large projects may have different phases running
     concurrently.  Use this to designate to which network or
     node this task belongs to.  For most projects, use the phase
     number. (The default value is the phase number)

Successor

     Use this field to define task dependencies. Refer to
     'Assigning Successors'.

Description

     Enter the description for this task. This description will
     appear on all reports and Gantt charts.

Milestone

     Milestones reflect major project accomplishments.  If this
     task is considered a milestone in the project, enter a 'Y'.

Resource

     Enter the resource code for the resource assigned to this
     task.  A maximum of four different resources may be assigned
     to a particular task.

Est. Time

     Enter the amount of estimated time (hours or days) needed to
     complete this task.



Time To-Date                                                             14

     Enter the amount of time this resource has spent thus far
     wordking on this task.

New Est

     Enter the revised estimated time to complete this task.

Planned Start/Stop

     Enter the original or planned start and stop date for this
     task.

Actual Start/Stop

     Enter the actual or projected start and stop date for this
     task.

Fixed Date

     Enter a 'Y' if the dates associated with this task cannot be
     changed for any reason.  This is useful for vacation use.

Status

     This will designate the status for this task.  When
     completed, use a 'C'.

Note 1 & Note 2

     To be used for any purpose.

Entering Tasks

     Every task number consists of the following elements:

     Task Number  - 2 character phase number (01-20) plus
                    4 character task number (user defined)
     Item Number  - 2 characters, user defined (optional)
     Successor    - 8 characters, made up of (Phase + Task +
     Item)

     Keep in mind that most reports are produced in task number
     order. Using sequential task numbers of 0001, 0002, etc.
     within each phase is recommended.

     'Item' is designated as a subordinate task.  This is an
     optional entry but is useful in breaking down a large main
     task.  Again, it's useful to use sequential item numbers
     within each task number.




Assigning Successors                                                     15

     If a task cannot begin until the previous task is complete,
     enter the task number of the successor in the 'Successor'
     field of the current task.

     Example:  A phase has 4 tasks, 0001 through 0004.  Every
     task is dependent upon the previous task.  The tasks should
     be established as follows:

                       Task              Successor

                       01-0001            01-0002
                       01-0002            01-0003
                       01-0003            01-0004
                       01-0004            01-0004

     If tasks can run concurrent with each other, set up the
     tasks in this manner:

                       Task              Successor

                       01-0001            01-0002
                       01-0002            01-0002 --
                       01-0003            01-0003  | Concurrent
                       01-0004            01-0005 --    Tasks
                       01-0005            01-0005


Sample Task Numbers

     Task Field  =  01-0001
     Item Field  =  01
     Successor   =  01-0001-02

     Example:  This task belongs to Phase 1, Task equals 0001 and
     this is the first item for task 0001. Task/Item 01-0001-02
     cannot start until this task is complete. 01-0002-01 is
     placed in the 'Successor' field.


     Task Field  = 01-0003
     Item Field  = <blank>
     Successor   = 01-0003

     Example:  This task belongs to Phase 1, Task equals 0003 and
     there are no subordinate items.  No other task is dependent
     upon this task so the 'Successor' field defaults to itself.




Automatic Schedule Maintenance                                           16

     If a planned start or stop date is changed, for an existing
     task, the automatic scheduler will be invoked (based on
     parameter setting in System Configuration) adjusting both
     planned and actual start and stop dates for the succeeding
     tasks. You will have the ability to override the proposed
     dates. Likewise, if a current start or stop date is changed,
     the automatic scheduler will be invoked to adjust current
     dates only.

Marking Tasks Complete

     For the purpose of the Project Status Report and the Gantt
     chart, a status of 'C' denotes that a task is complete.  For
     other purposes, any other code may be used.


Quick-Input                                                             17

To add tasks to a project in a simple and fast method, try this
option.  The 'Quick-Input' option will permit 19 tasks to be
entered from one screen.  The following limitations currently
exist when using this screen:

      Planned or actual dates cannot be entered (use the
     Schedule option)

      Milestone, Fixed Dates, Notes or Status fields cannot be
     entered

      The estimated time entered is applied to Resource 1 only



==QUICK INPUT SCREEN==



Any tasks entered here, can be maintained like any other task via
the Task Parameter screen.




Automatic Schedule Generation                                           18

Easy Project will automatically calculate planned start and stop
dates based on the estimated time assigned to each task.

To calculate dates, first choose 'Schedule' from the Main Menu.
Next, enter the project number followed by the base start date.
The base start date should be the date the project may begin.

Schedule Screen Display

As the schedule generates, each task and the newly calculated
dates are displayed.  After the screen fills, you have the
ability to change or override the calculated date.  Pressing
<ESC> aborts the update process and the records will not be
updated.

Use the <ENTER> key to advance the cursor.  When the screen is
completely updated, these dates will be used to update both the
planned and the actual start and stop dates for the tasks.

The <PgDn> key will accept all dates and advance to the next
screen.

==SCHEDULE SCREEN==

Calculate Critical Path Only

     In the case of projects with concurrent phases, you may want
     to calculate the critical path of the project.  The critical
     path will be the longest phase or network in time duration.
     Setting this option to 'Y' will not calculate any new dates.

Schedule Networks Parallel

     If this option is set to 'Y', each phase or network will be
     scheduled from the project start date.  This permits
     multiple phases to be scheduled at the same time.

Notes on Scheduling

     1.  In the case of multiple resource tasks, the resource
     taking the greatest amount of time will be used in
     calculating the schedule. (the display reflects this)

     2.  Any task which has a Fixed type resource will be ignored
     for scheduling purposes.

     3.  On the Resource Parameter screen, the Usage field should
     reflect the total number of hours the resource works in one
     day. Use this for both hourly and daily type resources.

     4.  Weekends will be taken into consideration when
     calculating the schedule based on the option chosen from the
     Project Parameter screen.

     5.  If a task was set up with the Fixed Date option set, the
     fixed date will be used instead of the calculated date.

Gantt Chart                                                             19

Easy Project's Gantt charts are designed to give a graphic
display of a projects planned vs. actual progress.



==GANTT CHART==



Two different types of charts may be produced:

     1.  A chart displaying tasks for one particular phase in
     task number order.

     2.  A chart displaying the entire project with tasks grouped
     by dependencies.

     NOTE:  In order for a task to be displayed, it must have a
     Planned Start Date and Planned Stop Date.

Scale Options

     Flexible Gantt scales can be chosen to insure the most
     complete view of a project.  Each symbol on the chart can
     represent from 1 to 6 days or 1 to 6 weeks.  For projects of
     short duration, a scale in days is probably more
     appropriate.


Output Options

     Easy Project offers three output options for producing
     Gantt charts:

          1.  (D)isplay - The chart will be displayed on your
          monitor.

          2.  (P)rint - The chart will be routed to your printer.
          By printing in a compressed format, a longer view will
          be produced.

          3.  (F)ile -  The chart will be written to a disk file
          using the default file name of GANTT.PRN.  This is an
          ASCII text file that may be printed through DOS or
          another printing utility.  By using either a wide
          carriage printer or a sideways printing utility, an
          even longer view may be produced.



Gantt Chart Symbols                                                      20

        =      Planned Date
        |      Actual Date
        *      Completed Task
        M      Milestone
        CRIT!  Critical Task
        <--    Task has start date prior to beginning of scale
        +      Task has multiple resource assignments



Reports                                                                 21


Many helpful reports may be instantly displayed, printed or
written to a disk file for later editing by your favorite word
processor. Some reports are printed in compressed format - thus
giving more detail than when displayed.  The actual title of each
report is enclosed in ( ).  Check the Appendix for samples of all
reports.


     Work Plan By Task

     (Phase Work Plan) - Produces a detailed work plan for a
     particular phase in task number order. [prints compressed]


     Work Plan By Resource

     (Phase Work Plan) - Produces a detailed work plan for the
     entire project by resource assignment.  [prints compressed]


     Work Plan Project Summary

     (Project Work Plan Summary) - Summarizes all phases of a
     project plan giving a concise report.


     Work Plan Resource Summary

     (Project Resource Summary) - Produces a departmentalized
     resource summary for a particular phase or the entire
     project.


     Project Status Report - Plan vs. Actual

     (Project Status Report) - A status report for the entire
     project detailing cost and schedule variances.  [prints
     compressed]


     Project Status Summary - Actual

     (Project Work Plan Summary) - Summarizes all project phases
     showing actual costs and current schedule dates. [prints
     compressed]


     Project Resource Summary - Actual

     (Project Resource Summary) - Produces departmental break
     down of actual costs by individual resource.



     Earned Value Report                                                 22

     (Earned Value Report)
     A report detailing project cost accruals. [prints
     compressed]


     Resource List

     (Project Resource List) - A detailed list of all resources
     assigned to a particular project.


     Work Plan - All Projects

     (Resource Work Plan - All Projects) - A detailed resource
     plan using all active projects.  This report will be helpful
     in identifing resource conflicts. [prints compressed]


NOTE:  Remember that Easy Project files are dBASE compatible and
can be read directly by many other applications.  It is possible
to create your own custom reports either by using the .DBF files
or using one of the above reports, choosing the 'F' (File)
option, and editing the ASCII file that is produced.





Utilities                                                               23

The Utility Menu consists of various functions that may be used
for file handling or system configuration.

NOTE:  Be sure to backup all Easy Project files on a regular
basis. This will help in recovering from any potential disasters.


     Reindex All Files

     Easy Project uses index files (.NTX) which permit fast data
     retrieval.  These index files are not compatible with dBASE
     .NDX files.  All files with the extension of .NTX should
     never be deleted. If file integrity is ever in question,
     choose the reindex option.

     NOTE:  It can never hurt the system to reindex files.


     Delete (Pack) Marked Records

     When task or resource data is deleted using the 'F5' key,
     the records are actually marked for deletion but physically
     remain on file.  These records are unavailable for normal
     use.  The delete option on this menu will physically delete
     all marked records.  Once this option is exercised, the
     marked records can no longer be used or recovered.


     Undelete (Recall) Records

     This option will find all records that have been marked for
     deletion (but not packed), and recall or make them available
     again for processing.

     NOTE:  This option will recall all records from all projects
     from all files regardless of project number.  Use this
     option with caution.


     Delete Project

     This function will delete all tasks, resources and related
     records for a particular project.

     To use, first enter the project number to delete.  Next, you
     will be prompted to verify that you really want to delete
     the project.  Answering 'N' will bypass any deletions.  If
     verified, records are then marked for deletion.

     Copy or Clone Project

     On occasion, you may want to create a project that has many
     similar tasks as another previous project. This copy option
     will copy a current project and duplicate all tasks and
     resources using a new project number.  The old project
     remains intact without changes.


     Copy or Clone Resources                                             24

     This option will copy current resources from one project and
     duplicate them using a new project number.  The old project
     remains intact without changes.


     Rebuild Files from Importing

     Easy Project database files (.DBF) are dBASE compatible and
     can be imported by many other applications.  Exporting files
     to other software packages may provide useful for additional
     reporting or mass updating.

     If files are updated outside of Easy Project, they must be
     rebuilt.  This function will automatically rebuild index
     files and all necessary relations.

     NOTE:  Exercise caution when updating Easy Project files
     from outside applications.  Be sure to have recent backups
     of all files as a safeguard.


     Backup Data Files

     On a regular and consistent basis, backups should be made of
     Easy Project files.  This option will copy all databases
     (.DBF) to a floppy disk.  If you are using a two floppy
     system, use drive A as the target or destination drive.

     If files are restored from a backup, be sure to use the
     'Rebuild' option to maintain file integrity.

     NOTE:  This function copies only data (.DBF) files.  Regular
     backups of all Easy Project files should be made using the
     DOS COPY, XCOPY or DISKCOPY commands.


     Configure System

     This option sets the proper type of monitor for your system,
     the proper destination for printer output, Gantt chart
     display option and automatic scheduling options.  Also,
     several different date formats may be chosen.
     Configure Printer

     Easy Project supports many printers.  Find the number that
     corresponds to your printer and enter the number at the
     prompt.  If your printer is not listed, try either the
     I.B.M. Graphics or Other ASCII Printer.  Give us a call if
     your printer is not listed here or if you are having
     unsatisfactory results.





Conclusion                                                            25


Easy Project is a dynamic system that is constantly being
enhanced.  Your suggestions and comments are greatly appreciated.

Our users are our greatest source of new ideas.

If you have any questions about Easy Project, please contact us
by mail, phone, our BBS, or via CompuServe EasyPlex.

If you are a registered user, THANKS!  If not, please remember to
register if you find yourself using Easy Project.  Licensed users
receive:

       Latest version of Easy Project with Shareware screen disabled

       Printed User Manual with sample screens, reports and Gantt charts

       Notification of updates

       Free technical support

       Special BBS access


Thanks for using Easy Project!








                         A P P E N D I X



            Shareware Distribution

            Sample Reports (REGISTERED VERSION ONLY)

            Registration Form

            Index



                     SHAREWARE DISTRIBUTION



It is our view that Shareware constitutes a viable, low cost
alternative to many commercial programs.  Shareware's greatest
strength lies in the ability to try it before purchasing it.  We
also believe that Shareware is maturing as a distribution method
and that its quality and functionality is improving at a rapid
rate.  This could only happen because users, hopefully like
yourself, are supporting Shareware products by remitting their
registrations.

We hope our product continues to be a productive element of your
system and we urge you to consider other Shareware products when
you decide to add software to your system.

Parcell Software is a member of the Association of Shareware
Professionals (ASP).  ASP wants to make sure that the shareware
principle works for you. If you are unable to resolve a
shareware-related problem with an ASP member by contacting the
member directly, ASP may be able to help. The ASP Ombudsman can
help you resolve a dispute or problem with an ASP member, but
does not provide technical support for members' products. Please
write to the ASP Ombudsman at P.O. Box 5786, Bellevue, WA 98006
or send a Compuserve message via easyplex to ASP Ombudsman
70007,3536.



















                     E A S Y  P R O J E C T

                        Registration Form

The license fee for Easy Project is $49.00 (U.S. FUNDS ONLY).
The license covers use on one PC only.  Multiple copies must be
purchased for use on multiple PC's.  Quantity discounts and site
licenses are available.  Contact us for further information.

    Method of Payment:
             Check (DRAWN ON U.S. BANK ONLY)

             Purchase Order (Government, Schools, Fortune 1000)

             VISA       --|
                          |  Phone order accepted: (708) 232-6328
             Mastercard --|

                Card Number:

                Expiration Date:

                Name on Card:

                Phone Number:

                Signature:

SHIP TO:

    Name:                                     Date:

    Company:

    Address:



Where did you learn about Easy Project?

    ----------------------------------------------------------
    Quantity| Description       | Unit Cost   |  Total Cost  |
    ----------------------------------------------------------
            | Easy Project 3.6  |   49.00     |              |
    ----------------------------------------------------------
    Shipping (outside U.S.A. only)   5.00     |              |
    ----------------------------------------------------------
              Total Payment:                  |              |
                                              ----------------
              Mail Order to:
                        Parcell Software
                          P.O. Box 165
                        Geneva, Il  60134
                             U.S.A.

                           I N D E X


Code
     resource. . . . . . . . . . . . . . . . . . . . . . . . . 14
CONFIG.SYS File. . . . . . . . . . . . . . . . . . . . . . . . .4
Critical Path. . . . . . . . . . . . . . . . . . . . . . . . . 18
Date
     actual. . . . . . . . . . . . . . . . . . . . . . . . . . 17
     fixed . . . . . . . . . . . . . . . . . . . . . . . . . . 17
     planned . . . . . . . . . . . . . . . . . . . . . . . . . 17
Delete . . . . . . . . . . . . . . . . . . . . . . . . . . . . 23
     Resource. . . . . . . . . . . . . . . . . . . . . . . . . .7
     task. . . . . . . . . . . . . . . . . . . . . . . . . . . .7
Delete Project
     project . . . . . . . . . . . . . . . . . . . . . . . . . 23
Dept
     resource. . . . . . . . . . . . . . . . . . . . . . . . . 14
Description. . . . . . . . . . . . . . . . . . . . . . . . . . 16
DOS. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .9
Exit . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .9
F1 Key . . . . . . . . . . . . . . . . . . . . . . . . . 8, 9, 14
Gantt. . . . . . . . . . . . . . . . . . . . . . . . . . . . . .9
Gantt Chart. . . . . . . . . . . . . . . . . . . . . . . . . . 19
     output options. . . . . . . . . . . . . . . . . . . . . . 23
     scale options . . . . . . . . . . . . . . . . . . . . . . 23
     symbols . . . . . . . . . . . . . . . . . . . . . . . . . 24
Help . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .7
Importing. . . . . . . . . . . . . . . . . . . . . . . . . . . 23
Installation . . . . . . . . . . . . . . . . . . . . . . . . . .5
Item number. . . . . . . . . . . . . . . . . . . . . . . . . . 16
Keyboard . . . . . . . . . . . . . . . . . . . . . . . . . . . .7
License. . . . . . . . . . . . . . . . . . . . . . . . . . . . .7
Main Menu. . . . . . . . . . . . . . . . . . . . . . . . . . . .9
Maintenance
     Resource. . . . . . . . . . . . . . . . . . . . . . . . . 14
Name
     resource. . . . . . . . . . . . . . . . . . . . . . . . . 14
Network. . . . . . . . . . . . . . . . . . . . . . . . . . . . 16
Non-Schedule Days. . . . . . . . . . . . . . . . . . . . . . . 13
Note 1
     resource. . . . . . . . . . . . . . . . . . . . . . . . . 15
Note 2
     resource. . . . . . . . . . . . . . . . . . . . . . . . . 15
Phase Descriptions . . . . . . . . . . . . . . . . . . . . . . 13
Printer
     configure . . . . . . . . . . . . . . . . . . . . . . . . 24
Project. . . . . . . . . . . . . . . . . . . . . . . . . . . . .9
     clone . . . . . . . . . . . . . . . . . . . . . . . . . . 23
Project Description. . . . . . . . . . . . . . . . . . . . . . 9
Project Name . . . . . . . . . . . . . . . . . . . . . . . . . 9
Project Number . . . . . . . . . . . . . . . . . . . . . . . . 9
Project Parameters . . . . . . . . . . . . . . . . . . . . . . 9
Quick-input. . . . . . . . . . . . . . . . . . . . . . . . .9, 20
Rate . . . . . . . . . . . . . . . . . . . . . . . . . . . . . 14
Registration . . . . . . . . . . . . . . . . . . . . . . . . . .7
Reindex. . . . . . . . . . . . . . . . . . . . . . . . . . . . 23

                           I N D E X


RepOrts. . . . . . . . . . . . . . . . . . . . . . . . . . .9, 21
Resource . . . . . . . . . . . . . . . . . . . . . . . . . .9, 17
     clone . . . . . . . . . . . . . . . . . . . . . . . . . . 23
Sample . . . . . . . . . . . . . . . . . . . . . . . . . . .4, 11
Schedule . . . . . . . . . . . . . . . . . . . . . . . . . . . .9
     generation. . . . . . . . . . . . . . . . . . . . . . . . 18
     screen display. . . . . . . . . . . . . . . . . . . . . . 18
Source
     resource. . . . . . . . . . . . . . . . . . . . . . . . . 15
Status . . . . . . . . . . . . . . . . . . . . . . . . . . . . 17
Successor. . . . . . . . . . . . . . . . . . . . . . . . . . . 16
Task . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .9
     assigning succesors . . . . . . . . . . . . . . . . . . . 15
     entering. . . . . . . . . . . . . . . . . . . . . . . . . 15
     numbers . . . . . . . . . . . . . . . . . . . . . . . . . 16
     schedule maintenance. . . . . . . . . . . . . . . . . . . 16
Task number. . . . . . . . . . . . . . . . . . . . . . . . . . 13
Task Parameters. . . . . . . . . . . . . . . . . . . . . . . . 13
Tasks
     completed . . . . . . . . . . . . . . . . . . . . . . . . 16
Time
     estimated . . . . . . . . . . . . . . . . . . . . . . . . 16
     new estimate. . . . . . . . . . . . . . . . . . . . . . . 17
     to-date . . . . . . . . . . . . . . . . . . . . . . . . . 17
Type
     resource. . . . . . . . . . . . . . . . . . . . . . . . . 14
Upgrading. . . . . . . . . . . . . . . . . . . . . . . . . . . .5
Usage. . . . . . . . . . . . . . . . . . . . . . . . . . . . . 14
Utilities. . . . . . . . . . . . . . . . . . . . . . . . . .9, 23
Weekends . . . . . . . . . . . . . . . . . . . . . . . . . . . 13