AnalytiPlan

Project Planner

PPLN*.* are a template project plan spreadsheet for AnalytiCalc. Load it

and use the AR command to add more rows as needed. The PPLN8CP.CMD file

can allow it to compute critical path and the PPLN8CP.CMD file draws a

graphical representation of activities vs. time on screen. This is version

0 of the software and may need some tweaking but seems basically usable. It

will display start and end dates of each activity on screen 1 and resource

use vs. time on screen 2 (switched by @PPLN8CP.CMD or @PPLN8P2.CMD commands).

Requirements are to enter activity names, durations (days), amount

of resources, and preconditions. Preconditions are cell names of the cells

with activity names (e.g., A3, A4, A5, etc., or more than one. They may be

separated by commas or ranges can be specified separated by colon, so that

A3,A5:A7,A11 is a legal set or preconditions. Activities can be entered in

any order.